## Use Case Points
Project size estimation
Unadjusted Actor Weight (UAW)
| Actor | Description |  |  | Complexity | Weight
| Inventory Manager | Vehicle status, new info, parking lots, and inventory queries |  |  | Complex | 3
| Customer | Queries the inventory and reserves a car |  |  | Complex | 3
| Salesperson | Queries inventory, update vehicle status, and find vehicles |  |  | Complex | 3
| Database | Holds all information of lots and vehicles |  |  | Complex | 3
| Sensor Device | reports occupancy status |  |  | Simple | 1
| Technician | find vehicle and updates vehicle status |  |  | Complex | 3
[5 empty] | TOTAL UAW: | 16
Unadjusted Use Case Weight (UUCW)
Use Case |  | Description |  |  | Transaction Count | Classification | Weight
UC-1 |  | Moderate Interface. 2 actors, 4 steps for success |  |  | 9 | Complex | 15
UC-2 |  | Moderate Interface, 4 actors, 4 steps |  |  | 14 | Complex | 15
UC-3 |  | Moderate Interface, 3 actors, 6 steps |  |  | 12 | Complex | 15
UC-4 |  | Moderate Interface, 3 actors, 8 steps |  |  | 12 | Complex | 15
UC-5 |  | Simple interface, 3 actors, 3 steps |  |  | 8 | Complex | 15
[6 empty] | TOTAL UUCW: | 75
Technical Complexity Factor (TCF)
| Factor | Description |  | Weight | Value | Subtotal
| T1 | Web-based System & Sensors |  | 2 | 5 | 10
| T2 | No performance Objectives |  | 1 | 0 | 0
| T3 | End-user expects faster car finding |  | 1 | 4 | 4
| T4 | Internal processing is simple |  | 1 | 0 | 0
| T5 | No requirement for re-usability |  | 1 | 0 | 0
| T6 | Easy to install |  | 0.5 | 4 | 2
| T7 | Easy to use |  | 0.5 | 5 | 2.5
| T8 | No portable goals |  | 2 | 0 | 0
| T9 | Easy to change |  | 1 | 3 | 3
| T10 | Concurrent use is required |  | 1 | 5 | 5
| T11 | Security is a concern |  | 1 | 4 | 4
| T12 | No access for third parties |  | 1 | 0 | 0
| T13 | No unique training |  | 1 | 1 | 1
[5 empty] | Total (TF): | 31.5
[5 empty] | TOTAL (TCF): | 0.915
Environment Complexity Factor (ECF)
Per the instructions, we are to assume this is 1 or equal to all other teams.
|  |  |  | TOTAL ECF: | 1
Use Case Points (UCP)
| Equation | UAW | UUCW | TCF | ECF
| UCP= (UAW + UUCW) x TCF x ECF | 16 | 75 | 0.915 | 1
| Total UCP: | 83.265